## Slide 1: Engine/APU Halon Replacement Industry Consortium – Halon Alternatives for Aircraft Propulsion Systems (HAAPS) - Update
October, 2019
FAA Fire and Cabin Safety 9th Triennial conference
Atlantic City, USA
Fernando Wright, Embraer
HAAPS Governance Board Member

## Slide 2: HAAPS Charter and Statement of Work
Define common non-halon fire extinguishing solution(s) for use in engine/APU fire
zones that…
  is compliant to basic industry and international regulatory requirements
  • meets multiple OEM (airframe, engine, APU, nacelle, etc.) requirements
  meets multiple governmental agency regulatory requirements;
  provides a viable business solution for Consortium partners and suppliers;
  is production-ready
Engage…
  Primary Stakeholders = Airframer OEMs
  • Firex Agents/System Suppliers, Airlines, engine companies,
nacelle suppliers, airworthiness authorities, etc.
  Focal point, facilitator & fiscal/contracting administrator “Managing Entity” (ME)

## Slide 3: HAAPS Organization Halon Alternatives for Aircraft Propulsion Systems (HAAPS)
Governing Members
Airbus
Boeing
Bombardier
Embraer
Textron, Inc.
OAI
Project Teams
Established by GB
Prepare proposals in response to GB defined requirements and relevant funding opportunities
Resources, cost share commitment (as appropriate)
Execute funded projects
Share results through GB
Technical Direction
Governance Board (GB)
Strategy, Advocacy
Consortium Oversight
Approve Participants
Budgets, Funding Allocation
Define Project Requirements / Selection
Product Integration
Industry and Advisor Members
Airworthiness Certification Authorities
Environmental regulatory authorities
Aircraft Operators
Aircraft Component OEMs
Extinguisher system suppliers
Universities
Consultants
Other Stakeholders
Administrator
Ohio Aerospace Institute (ME)
Fiscal, legal representative
Day-to-day Administrative & Contract Mgmt.
Facilitator
Negotiated Agreements
(as appropriate)
Joint Collaboration Agreement (JCA)

## Slide 4: HAAPS Critical Milestones
Year 1 – Phase II | Year 1 - Phase III | Year 2 – Phase III | Year 3 – Phase III
RFI to Suppliers – End Oct 2018
RFI Response Evaluations & Preliminary Down Selection Workshop (March 25-28, 2019)
Certification Path Proposals Development
High Level Request For Information (RFI)
1st Down Selection (“Step 1” RFI)
Solutions(s) Requirements Definition
Detailed RFI (“Step 2” RFI)
Downselect Finalists for In-Depth Evaluation in Phase III
Phase III Statement of Work Definition
Technical Readiness Level (TRL) Defined
Agreements with Supplier(s)
Phase III (3 Years Maximum)
Phase II (1 Year Maximum)
HAAPS/FAA Familiarization
Meeting (Sept. 26 2018)
Final Solutions(s) Developed - END PHASE III
(2 to 3 year after phase III beginning)
In-Depth Evaluations of Downselected Candidates
  Extinguishing performance, qualification requirements, weight/volume impact, Material compatibility, certification path refinement, certification documentation development, environmental & health acceptability, new/restarted testing, etc.
Post-HAAPS – Solution(s) Incorporation (TRL 9)
Air framer member’s independent certification activities
Utilize HAAPS Certification Path, MOCs agreements, test and qualification data, etc. and other to support airplane integration
Formal Start to Phase II* - 15 Oct. 2018
Workshop at Montreal – Oct. 2019
Phase II Down Selection process by the end of 2019
Contractual work to be finalized by Feb 2020
Phase III est. Start by Feb 2020
Notes: “Documentation of analyses, testing, etc. …” : Examples include, but are not limited to materials compatibility, toxicity, MPSHRe results, FAA acceptability of minimum concentration measurement technology, etc.. that will be used to support the certification MOCs.

## Slide 5: HAAPS Charter and Statement of Work
Phase I – Joint Collaboration Agreement (JCA)
  Primary working together agreement signed June 2018
    Airbus, Boeing, Bombardier, Embraer, Textron, and Ohio Aerospace Institute
Phase II – Development of Technical Statement of Work & Industry Engagement
  Potential suppliers engaged
  Requirements detail and refinement
  Down selection process on-going
Phase III – execute activities required to produce acceptable solution(s)
    • Solicitation of selected supplier (s) final proposals
    • Proposal evaluation and down selection
    MOC/MeOC agreement
  • Testing & analyses
  • Selected solution(s) agreement
  Discussions with certification authorities in regards to final solution
COMPLETED
In progress
Formal Start est. Feb 2020
Notes: MeOC = Method of Compliance
MOC = Means of Compliance Code

## Slide 6: HAAPS Charter and Statement of Work
Phase II – Development of Technical Statement of Work & Industry Engagement
  COMPLETE
  Design Requirements Document – Initial Issue
    General & gaseous agent requirements
  Initial FAA Engagement
  Phase II supplier engagement documentation (PIAs, RFIs)
  Reviewed potential candidate supplier initial proposed solutions received by HAAPS.
  IN DEVELOPMENT
  High level solution(s) strategy
  Other agent types
  Performance validation, down selection criteria ongoing
  Compile Regulatory Requirements & Develop Certification Path Proposals
  Follow-up certification authorities engagement
  Phase III supplier engagement documentation
  Phase III schedule/TASK preparation
Notes: High Level Solutions Strategy: Agreement amongst OEM air framers on solution(s) priority rankings for evaluation as a function of numerous factors: agent development maturity, status of MPSHRe, overall schedule to selection, qualification costs, environmental approvals status, etc. .

## Slide 7: HAAPS Charter and Statement of Work
Phase II – Development of Technical Statement of Work & Industry Engagement
  RFI to Suppliers – “Step 1” COMPLETE
    Requested high level information on proposed Solution(s) candidates
    Numerous preliminary RFIs transmitted
      Firex system suppliers, firex agent suppliers, firex distributors, chemical companies
    Downselected to approximately 10-12 potential solutions
  Follow-on RFI sent to Selected Suppliers – “Step 2” COMPLETE
    Evaluates downselected solutions from “Step 1” in greater detail
      Conformance to HAAPS Design Requirements Document
      Encouraged to include proprietary information (protected by PIA)
  Down Selection of “Step 2” Solutions Proposals In progress
    Successful proposals move into Phase III evaluations
      Business agreements, statement of work definition, deliverables responsibilities, schedules

## Slide 8: Down Selection Process - Status
More than 40 potential global suppliers identified;
  From chemical companies to aerospace suppliers;
Majority were contacted who demonstrated interest
  subset received an initial RFI with the HAAPS requirements document;
After several GB reviews and potential supplier telecons, approximately 10 suppliers signed PIAs and now are being evaluated in more depth by GB based on second RFI submittal which provided more details;
No more than 3 finalists to be selected for phase III
  expected by the end of 2019.
  COMPLETE
  COMPLETE
  COMPLETE
  In progress

## Slide 9: Contacts, Announcements & History
Ohio Aerospace Institute (OAI) http://www.oai.org/
  Don Bailey, HAAPS Project Manager DonBailey@oai.org , Phone: 440- 962-3050
OAI’s HAAPS Press Release – Phase I
  http://web1.oai.org/oaiweb.nsf/wnews/B16B96B2AFB1763D85257DD9004F0B28?OpenDocument&sc=2
OAI’s HAAPS Press Release – Phase II
  https://www.prnewswire.com/news-releases/haaps-consortium-seeks-replacement-for-halon-1301-300817203.html?tc=eml_cleartime
ICCAIA Support of HAAPS Consortium
  http://www.aia-aerospace.org/news/iccaia-supports-international-consortium-seeking-alternatives-to-halon-fire-suppressant/
IASFPWG Meeting, Cologne, Germany, May 22-23, 2013 – Consortium Proposal
  https://www.fire.tc.faa.gov/pdf/systems/May13Meeting/BennettMacias-0513-ICInterestEgineAPU.pdf
Halon Alternatives Research Corporation (HARC) sponsored Aviation Stakeholder's Meeting Chicago, Illinois, U.S.A., 11 June, 2013 – Consortium Proposal
2013 ICAO Assembly recognized consortium commitment , Resolution 31/1: Halon
replacement (link)

## Slide 10
Thank you!